## Gantt Chart
Project Methodology
Course assignment: Project planning, process documenting and collaboration
Gantt Chart for website
Client: Lofthus frukt og saft
They need a new website as part of their ambitions to find new markets, promote and sell their products.
Estimated time for project: 6 WEEKS
Project participants: | Project manager
Content manager
Developer
Designer
Copywriter
Photographer
Shared files and project in: Trello business
|  |  | PLANNING |  |  |  |  | DESIGNING AND BUILDING | [14 empty] | TESTING |  |  |  |  | LAUNCH
Tasks | Who | hours | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
|  |  | M | T | O | T | R | M | T | O | T | R | M | T | O | T | R | M | T | O | T | R | M | T | O | T | R | M | T | O | T | R
Research client | Project manager | 2 | bar: WEEK 1 M
Client meeting | Project manager, Content manager | 3 | bar: WEEK 1 M
Meeting to confirm and deside on project plan | Project manager, Content manager, developer, designer | 4 | bar: WEEK 1 T
Research: Competition, current market for juice and fruite and possibilities through new site | Content manager, designer | 15 | bar: WEEK 1 O to WEEK 1 T
Technical check of old website | Developer | 7,5 | bar: WEEK 1 T
Plan content and strategy | Developer, designer, content manager | 15 | bar: WEEK 1 R to WEEK 2 M
Client contact | project manager, Content manager | 3 | bar: WEEK 2 T
Create sitemap for content structure and documentation describing features | Developer, designer | 21,5 | bar: WEEK 2 T to WEEK 2 T
Create styletile / moodboard | Designer | 7,5 | bar: WEEK 2 T
Layout | Designer | 21,5 | bar: WEEK 2 T to WEEK 3 M
Create design ellements with the logo and brand in mind | Designer | 15 | bar: WEEK 3 T to WEEK 3 O
Write text / articles | Copywriter | 37,5 | bar: WEEK 2 T to WEEK 3 O
Product and environment photoshoot | Photographer | 37,5 | bar: WEEK 2 T to WEEK 3 O
Photoediting | photographer, designer | 15 | bar: WEEK 3 T to WEEK 3 R
Client contact | Project manager, Content manager | 3 | bar: WEEK 4 M
Wireframe | Developer | 21,5 | bar: WEEK 2 R to WEEK 3 T
coding, integration and site build | Developer | 60 | bar: WEEK 3 O to WEEK 4 R
Testing for UX | Developer, designer | 15 | bar: WEEK 5 M to WEEK 5 T
Testing across platforms and browsers | Developer | 15 | bar: WEEK 5 O to WEEK 5 T
Client contact | Project manager | 7,5 | bar: WEEK 5 T
Validating | Developer | 7,5 | bar: WEEK 5 R
Refinment | Developer, designer, content manager | 7,5 | bar: WEEK 6 M
Launch | Project manager, content manager, designer, developer | 7,5 | bar: WEEK 6 T
| Hours spent total | 165